## Tina
Month | Week | Activities | Description | In Progress | Done | Link
8 | 4 | NSF/SIT Final Presentation |  |  | v
| 3 | NSF/SIT Project Report & Poster | Prepare final project report and poster |  | v
| 2 | SMO-B Implementation | Evaluate and assess performance against baselines | v |  | https://drive.google.com/file/d/0BzMzlyPKq2NMTVhMbmt1c1dxYUE/view?usp=sharing
|  | NSF/SIT Project Report & Poster | Closed Bicluster Algorithm Matlab program |  | v | https://drive.google.com/file/d/0BzMzlyPKq2NMOWRLcGExQW5mY1k/view?usp=sharing
| 1 | Implement Spider Monkey Optimization based Biclulstering Method (SMO-B) | SMO-B cluster formation | v |  | https://drive.google.com/file/d/0BzMzlyPKq2NMSEhwUkNlZU5HdWc/view?usp=sharing
|  |  | Fitness function (Matlab) |  | v | https://drive.google.com/file/d/0BzMzlyPKq2NMeGNMcnMyVUFKRnc/view?usp=sharing
|  |  | Biclustering baseline methods (BiMAX, ISA, FABIA) |  | v | http://link.springer.com/article/10.1007/s12293-013-0128-0
7 | 4 | Data Preprocessing | Data filtering and cleaning |  | v | https://drive.google.com/open?id=0BzMzlyPKq2NMaElmSS1vMGdfOWs
https://drive.google.com/file/d/0BzMzlyPKq2NMS2pNcjBiNjVwMmM/view?usp=sharing
| 3 | Data Collection | GSE3141, GSE8894, GSE10245, GSE10445, GSE11969, GSE19804 |  | v | https://goo.gl/fnlrnb
| 2 | Literature Review | Lung cancer in general. Causes, syndromes, DNA/genes |  | v
| 1 | Desktop/PC Setup | MATLAB, Python, Weka3, R and some statistical packages |  | v
6 | 4 | NSF/SIT Orientation Week |  |  | v